## Sheet1
ID | Objective | Information Required | Source | Technique | Questions / Topics | Expected Output | Priority | Status
EL-001 | Understand business problem | When/why completion declined | Project Sponsor | Interview | Why did completion fall from 72% to 54%? When did it begin? What business impact has occurred? What outcome does management expect? | Confirmed business problem, objective, target KPIs, business impact | High | Planned
EL-002 | Understand current process | Application steps, handoffs, failure points | Operations | Interview + Observation | What are the current application steps? Who/system performs each step? Where are handoffs, delays, errors and decision points? What happens when an upload fails? | AS-IS process map/BPMN, pain points, failure points, handoffs | High | Planned
EL-003 | Identify customer pain points | Errors, abandonment points, recovery behavior | Customers | Interview / Survey | Where do customers struggle? What errors do they encounter? Why do they abandon? Can they recover? Are mobile and web experiences different? | Customer pain points, abandonment reasons, UX findings | High | Planned
EL-004 | Understand compliance impact | Document rules, validation, re-validation | Compliance SME | SME Interview | What documents require validation? What defines a "same document"? When can validation be reused? When is re-validation mandatory? What compliance rules apply? | Compliance business rules, validation/re-validation criteria, control requirements | High | Planned
EL-005 | Identify technical causes | Upload failures, latency, timeout behavior | Technology Lead | Technical Interview | What changed in the latest release? Where exactly does upload fail? Are there latency/API/server issues? How does timeout work? What happens during retry? | Technical findings, system constraints, failure points, integration dependencies | High | Planned
EL-006 | Validate performance issue | Completion, upload, timeout and processing metrics | Data/System | Data Analysis | How did completion, abandonment, upload failures, upload duration, timeouts and compliance-processing time change before vs. after release? | Quantitative analysis, trends, correlations, supporting evidence | High | Planned
EL-007 | Understand operational impact | Workarounds, incidents, support issues | Operations | Interview | What production issues increased? What workarounds are employees using? What support incidents are occurring? What operational impact exists? | Operational pain points, incidents, workarounds, support requirements | Medium | Planned
EL-008 | Identify solution constraints | Technical limitations and integrations | Technology Lead | Workshop | Can the proposed solution be implemented? What systems/integrations are affected? What technical limitations exist? What alternatives are possible? | Feasibility assessment, technical constraints, dependencies, solution options | High | Planned
EL-009 | Define acceptance expectations | Business acceptance criteria | Product Owner / QA | Workshop | What must the solution do to be accepted? What scenarios must pass? What are the acceptance criteria? What constitutes successful UAT? | Acceptance criteria, UAT scenarios, expected system behavior | High | Planned
EL-010 | Validate findings | Confirm root cause and business interpretation | Key Stakeholders | Playback Workshop | Do stakeholders agree with the findings? Is the identified root cause accurate? Are any assumptions or gaps remaining? | Validated findings, stakeholder sign-off/feedback, unresolved questions | High | Planned
EL-011 | Identify stakeholder priorities and conflicts | Business value, compliance, technical, operational and customer priorities | Sponsor, Product Owner, Compliance, Technology, Operations | Workshop + Interviews | What does each stakeholder prioritize? Where do business, compliance, technology, operations and customer needs conflict? What should be prioritized? | Stakeholder priorities, conflicts, decision criteria, prioritization inputs | High | Planned