PROJECT CHARTER

Digital Loan Application Optimization

Northstar Financial Services | Business Analysis Portfolio Project

# 1. Project Overview

Northstar Financial Services has identified a significant decline in customers completing its online loan application. This project will investigate the current application journey, identify evidence-based causes of abandonment, and recommend improvements while maintaining existing compliance and fraud-control requirements.

# 2. Business Problem

Online loan application completion has declined from 72% to 54%, creating increased application abandonment and longer customer processing times.

# 3. Business Objective

Increase online loan application completion from 54% to at least 70% while reducing application processing time toward an agreed management target, without weakening existing compliance or fraud-control requirements.

# 4. Scope

## 4.1 In Scope

Online loan application process from application start/resume through submission.

Application completion and abandonment.

Application processing time and customer waiting time.

Document upload and document-processing activities.

Compliance-related processing within the online application journey.

Application errors, upload failures, and session timeouts.

Analysis of application data and process performance.

Identification and validation of root causes.

Recommendations for process and/or system improvements.

## 4.2 Out of Scope

Changes to underlying fraud or compliance policies themselves.

Changes to loan eligibility or underwriting policy.

The broader loan processing lifecycle after the defined application scope.

Offline loan application channels.

Implementation of a specific technical solution before analysis and requirements validation.

# 5. Key Stakeholders

| Stakeholder | Role | Initial Interest |
| --- | --- | --- |
| Project Sponsor | Provides direction and funding/authority | Business outcome and value |
| Project Manager | Coordinates project delivery | Scope, schedule and delivery |
| Business Analyst | Investigates problem and defines requirements | Evidence, requirements and solution alignment |
| Product/Business Owner | Owns business process/product outcomes | Customer experience and completion |
| Compliance SME | Validates compliance requirements | Regulatory/control integrity |
| Technology Lead | Assesses technical feasibility | System constraints and implementation |
| Operations | Runs/ supports loan operations | Operational efficiency |
| QA/Test Team | Validates solution behavior | Testability and acceptance |
| Customers/End Users | Use the loan application | Ease, speed and successful completion |

# 6. Success Metrics

| Metric | Current Baseline | Target |
| --- | --- | --- |
| Application completion | 54% | ≥70% |
| Application processing time | To be validated | To be agreed |
| Compliance/fraud controls | Current baseline | No deterioration |

# 7. Known Constraints

Initial analysis and recommendation are expected within 12 weeks.

Existing compliance controls must be maintained.

Existing fraud controls must be maintained.

Recommendations must be supported by evidence and stakeholder validation.

# 8. Assumptions

Relevant application and system data will be available for analysis.

Key stakeholders and subject matter experts will be available for elicitation and validation.

Existing process and system documentation can be obtained or reconstructed where necessary.

Compliance and technology SMEs can validate findings and proposed requirements.

# 9. Initial Risks

The decline may have multiple interacting causes rather than a single root cause.

Data may be incomplete, inconsistent, or difficult to correlate across systems.

Proposed improvements may introduce compliance, fraud, security, or technical risks.

Stakeholders may have conflicting priorities.

Technical constraints may limit feasible solution options.

The 12-week timeline may constrain the scope of analysis or implementation.

# 10. High-Level Deliverables

Project Charter

Stakeholder Register and Stakeholder Analysis

Elicitation Plan and Findings

AS-IS Process Model

Data Analysis and KPI Findings

Root Cause / Evidence Analysis

Gap Analysis

TO-BE Process Model

Business, Functional and System Requirements

Business Rules and User Stories

Requirements Traceability Matrix

Change Request and Decision Analysis, where applicable

UAT/Test Scenarios and Test Cases

Final Business Recommendation

Post-implementation KPI / Outcome Analysis

# 11. Governance Note

This charter is an initial baseline and may be refined as discovery progresses. New information, validated stakeholder input, and approved scope changes will be recorded through the appropriate project artifacts.

# 12. Document Control

| Version | Date | Status | Prepared By |
| --- | --- | --- | --- |
| 1.0 | Initial Draft | Draft / Initiation | Kaoshal Rathod |