## 01_UAT_Execution_Log
Execution ID | Test Case ID | Requirement ID | Scenario | Expected Result | Actual Result / Evidence Summary | Status | Evidence Location | Executed By | Execution Date | Defect ID | Retest Status | Notes
EX-001 | TC-002 | FR-01 | Mandatory compliance validation | All mandatory validations execute; none are bypassed. | Audit log confirmed all required validations executed; no bypass observed. | Passed | Compliance validation audit log | QA / Compliance SME | 2026-10-10 | — | Not Required | Pass applies to this tested scenario.
EX-002 | TC-004 | FR-02 | Reuse after compliance-relevant change | Old result is not reused; fresh required validation executes. | System reused the previous result after loan details changed in a way that affects a compliance rule. | Failed | Audit log showing reused prior result | QA / Compliance SME | 2026-10-10 | DEF-001 | Not Run | Critical compliance defect; release blocker pending fix and retest.
EX-003 | TC-008 | FR-05 | Customer recovery | Customer resumes without restarting or re-entering saved information. | Customer resumed after temporary failure; saved information remained available. | Passed | Before/after application state and journey observation | QA / Product Owner | 2026-10-10 | — | Not Required | Does not prove all recovery paths pass.
EX-004 | TC-012 | NFR-01 | Peak-load waiting time | Waiting time meets approved target and measurement definition. | Observed wait was 13 seconds. Target and measurement definition have not been approved. | Blocked | Peak-load test report | QA / Technology Lead | 2026-10-10 | — | Pending Criteria | Do not mark pass/fail until criteria are approved.

## 02_Defect_Register
Defect ID | Execution ID | Test Case ID | Title | Reproduction / Description | Expected Result | Actual Result | Severity | Impact | Owner | Status | Fix Version | Retest Plan | Closure Evidence | Release Blocking?
DEF-001 | EX-002 | TC-004 | Stale compliance validation result reused | Start an application with a successful validation; change a loan/application attribute affecting a compliance rule; continue the workflow; inspect validation history. | Required fresh validation runs when a compliance-relevant attribute changes. | Prior validation result was reused after a compliance-relevant change. | S1 - Critical | Potential compliance control failure; application could proceed using a stale decision. | Technology Lead + Compliance SME | Open | TBD | Rerun TC-004 and related positive/negative validation-reuse regression tests. | Pending fix, audit evidence and successful retest | Yes

## 03_Release_Readiness
Item ID | Readiness Item | Current State | Required Action | Accountable Role | Status | Release Impact
RR-01 | Critical compliance defect DEF-001 | TC-004 failed; old result reused after relevant change | Fix root cause; run reuse regression tests; capture audit evidence; obtain Compliance approval | Technology Lead / Compliance SME | Open | Release blocker
RR-02 | Peak performance acceptance | Observed wait 13 seconds; target/measurement definition unapproved | Approve timing points, statistic/percentile, workload profile and target; then rerun/assess | Product Owner / Technology Lead | Blocked - criteria | Readiness unresolved
RR-03 | Compliance test TC-002 | Required validations executed in tested case | Retain audit log in regression evidence | QA / Compliance SME | Passed | Supports readiness
RR-04 | Recovery test TC-008 | Saved application information preserved during tested recovery | Retain evidence and test other applicable recovery paths | QA / Product Owner | Passed | Supports readiness
RR-05 | Release decision | BA recommendation is no release approval yet | Authorized release owner reviews blocker, performance criteria and sign-offs after retest | Release Owner | Pending | No-go until blocker resolved and criteria met

## 04_Usage_Guide
Topic | Guidance
Purpose | Record actual outcomes, evidence, linked defects, retesting and release-readiness actions.
Status rules | Passed: expected result met with evidence. Failed: approved expected result not met. Blocked: cannot judge because a prerequisite, approved criterion or environment is missing.
Severity | S1 - Critical is appropriate because a compliance-relevant change did not trigger required fresh validation; confirm against organizational defect policy.
Retesting | After a fix, create a new execution entry for the retest. Do not overwrite the original failed result.
Traceability | Keep Test Case ID, Requirement ID, Execution ID and Defect ID linked to the master RTM.
Evidence handling | Use controlled evidence IDs/links; avoid putting sensitive customer data directly in the workbook.
Release authority | The BA provides evidence and recommendation. The authorized release owner decides, with required Compliance approval.