## 01_Readiness_Assessment
Gate ID | Release Gate | Required Evidence | Current State | Status | Owner | Next Action | Release Impact
RG-01 | Mandatory compliance controls | Mandatory validations run; none bypassed. | TC-002 passed; TC-003, TC-004 and TC-015 passed after fix; Compliance SME verified audit logs. | Met - record sign-off | Compliance SME / QA | Attach execution IDs and formal Compliance approval. | Mandatory gate
RG-02 | Critical defect closure | Critical defects fixed, retested and closure evidence recorded. | DEF-001 fix passed TC-004; eligible reuse TC-003 and compliance regression TC-015 passed. | Met - record closure evidence | Technology / QA / Compliance | Record fix version, execution IDs, audit evidence and closure approval. | Blocker if not formally closed
RG-03 | Peak performance acceptance | Approved metric definition, target and successful peak-load evidence. | TC-012 observed 13 seconds; target and measurement definition remain unapproved. | Open - blocked | Product Owner / Technology / QA | Approve definition and target; execute/assess peak test. | Unresolved gate
RG-04 | Capacity and reliability | Approved peak workload/headroom and reliability criteria met. | Capacity/headroom and reliability thresholds remain unapproved/not evidenced. | Open - evidence needed | Technology Lead / QA | Approve criteria and attach test results. | Unresolved gate
RG-05 | Customer recovery | Applicable recovery scenarios pass and state is preserved. | TC-008 passed for tested transient recovery scenario. | Partially met | Product Owner / QA | Retain evidence and complete remaining recovery scenarios. | Check UAT exit criteria
RG-06 | Operations support | Operations can investigate unresolved failures with sufficient context. | TC-010 / UAT-05 not recorded as passed in current evidence. | Not yet evidenced | Operations / QA | Execute scenario and attach evidence. | Check UAT exit criteria
RG-07 | Customer messaging | Clear next action shown when automatic recovery cannot complete. | TC-009 / UAT-04 not recorded as passed in current evidence. | Not yet evidenced | Product Owner / QA | Execute scenario and obtain message approval. | Check UAT exit criteria
RG-08 | Business KPI | Completion KPI definition and reporting window approved; evidence comparable to baseline. | Goal is >70%; definition and measurement evidence need confirmation. | Open - evidence needed | Business Owner / BA | Confirm numerator, denominator, population, channel and window. | Benefit validation
RG-09 | Monitoring and rollback readiness | Alert thresholds, responders, escalation and rollback/traffic-reduction plan ready. | Safeguards proposed but readiness evidence not recorded. | Open - evidence needed | Technology / Operations / Release Owner | Document thresholds, owners, triggers and runbook. | Required for conditional release
RG-10 | Approvals and risk acceptance | Authorized release decision and required business/compliance approvals recorded. | Overall sign-offs not recorded in simulation. | Pending | Release Owner / Business Owner / Compliance | Confirm policy and record decision, accepted risk, owners and deadlines. | No approval yet

## 02_Risk_and_Exceptions
Risk ID | Risk / Exception | Evidence | Impact | Mitigation / Control | Owner | Due Date | Residual Risk Decision | Status
R-01 | Peak performance unaccepted | TC-012 observed 13 seconds; target undefined | Performance may be unacceptable at peak; abandonment may rise | Approve timing definition/target; run peak test; monitor latency, queue, upload failures and timeouts | Product Owner / Technology | TBD | Authorized release owner must assess; do not call test passed | Open
R-02 | Production degradation | Monitoring/rollback readiness not evidenced | Issues may persist before detection or recovery | Approved thresholds, named responders, escalation, rollback triggers and runbook | Technology / Operations | Before any conditional release | Pending evidence | Open
R-03 | Incomplete release approvals | Overall Business/Compliance sign-offs not recorded | Release may violate governance or compliance policy | Record approvals; confirm policy permits any deferred performance gate | Release Owner / Business / Compliance | Before decision | No acceptance inferred | Open
R-04 | Completion KPI definition | Target >70%; exact population/window needs confirmation | Success may be measured inconsistently | Approve numerator, denominator, reporting window and data source | Business Owner / BA | Before benefit claim | Pending definition | Open

## 03_Go_No_Go_Record
Field | Current Record
Project | Northstar Financial Services — Digital Loan Application Optimization
Assessment date | 2026-10-10
BA recommendation | Do not approve release yet. Conditional release may be considered only after policy review, required approvals and operational safeguards are evidenced.
Positive evidence | TC-002 passed; TC-003 eligible reuse passed; TC-004 passed after fix; TC-015 compliance regression passed; TC-008 tested recovery passed.
Open items | TC-012 blocked; performance target/definition unapproved; capacity/reliability criteria not confirmed; overall sign-offs missing; other UAT evidence requires confirmation.
Conditional release prerequisites | Confirm policy permits deferring performance acceptance; document risk; approve monitoring thresholds/responders; establish rollback plan; set owner/deadline for peak validation; obtain approvals.
Decision status | Pending — no release approval recorded
Decision owner | Authorized Release Owner
Business approval | Pending
Compliance approval | Pending
Technology readiness | Pending
Rationale | A blocked test is not a pass. Conditional release must not bypass mandatory compliance or required organizational release gates.