## 01_Test_Plan
Test Case ID | Requirement ID | Acceptance Criteria ID | Test Type | Scenario | Preconditions / Test Data | Test Steps / Action | Expected Result | Evidence to Capture | Owner | Priority | Status
TC-001 | BR-01 | AC-01 | Business KPI | Validate application completion against the agreed business target | Approved KPI definition, baseline, reporting window and representative production-like dataset are available | Calculate completion rate using the approved numerator, denominator, channel and reporting window | Completion rate exceeds 70% for the agreed measurement window; result is reported with sample size and comparison to baseline | KPI query/report, numerator and denominator, date range, sample size | Business Owner / BA | High | Blocked - KPI definition
TC-002 | FR-01 | AC-02 | Functional / Compliance | Mandatory compliance checks remain in force | Test cases cover all mandatory regulatory and compliance validations | Submit an application and complete the document workflow | Every mandatory validation executes at the required checkpoint; no path bypasses or suppresses a required control | Validation audit log, decision history, test execution record | Compliance SME / QA | Critical | Not Run
TC-003 | FR-02 | AC-03 | Functional | Reuse an eligible prior validation result for an unchanged document | Same document version; same applicable rule version; relevant application attributes unchanged; previous result valid; Compliance-approved reuse rules available | Trigger a workflow transition that would otherwise repeat the same validation | Prior result is reused only when all approved eligibility conditions are satisfied; reuse is auditable | Document/version identifiers, rule version, state comparison, audit log | Technology / Compliance / QA | High | Blocked - reuse rules
TC-004 | FR-02 | AC-04 | Negative / Compliance | Reject reuse when a compliance-relevant condition changes | Test data includes a changed document, relevant attribute, rule version, expired result and mandatory fresh-check checkpoint | Attempt to reuse a previous validation result after each change condition | Reuse is rejected and the required validation is run again | Before/after attributes, rule versions, validation history | Compliance SME / QA | Critical | Blocked - reuse rules
TC-005 | FR-03 | AC-05 | Functional / Performance | Avoid unnecessary duplicate document processing | Instrumented workflow with repeatable document and event identifiers | Run a journey with workflow transitions that do not change relevant document or compliance inputs | Duplicate processing is avoided where approved rules allow it; necessary processing still occurs | Processing event counts, document IDs/versions, timestamps | Technology / QA | High | Not Run
TC-006 | FR-04 | AC-06 | Negative / Recovery | Recover from a retryable transient processing failure | Fault injection can simulate a transient service error or temporary queue pressure | Submit a valid document while the transient failure is injected | System classifies the failure as retryable and follows the approved retry/backoff policy within configured limits | Error classification, retry count/timestamps, processing status | Technology / QA | High | Blocked - retry policy
TC-007 | FR-04 | AC-07 | Negative / Recovery | Do not blindly retry a non-retryable failure | Test data includes invalid/corrupt file, unsupported type, size limit violation and compliance failure | Submit each invalid document or trigger each non-retryable condition | System does not repeatedly retry non-retryable failures; customer and operations paths follow approved handling | Failure code, retry history, status/message | Technology / QA / Compliance | Critical | Blocked - failure taxonomy
TC-008 | FR-05 | AC-08 | End-to-end | Customer resumes after a retryable failure without restarting the application | Application has saved state and a retryable document-processing failure | Use the supported retry/recovery path after the transient fault clears | Customer can resume the journey without re-entering already saved application information; required validations remain enforced | Application state before/after, event log, screen recording | Product Owner / QA | High | Not Run
TC-009 | FR-06 | AC-09 | Usability / Recovery | Show a clear next action when automatic recovery cannot complete | Automatic recovery has exhausted approved attempts or the failure requires customer action | Trigger the unrecovered-failure state | Customer sees plain-language status and an actionable next step; saved application information is preserved | Message text, screenshot, state audit | Product Owner / QA | High | Blocked - message approval
TC-010 | FR-07 | AC-10 | Operations | Operations can investigate an unresolved processing failure | An unresolved failure exists with representative test identifiers | Open the operations view or case context and investigate the failure | Operations can see Application ID, Document ID/version, failure type, attempts, timestamps, processing status, error/reference ID, customer retry status and current application status, subject to access controls | Operations view, case record, access-control evidence | Operations / QA | High | Not Run
TC-011 | NFR-01 | AC-11 | Performance - Normal | Measure customer waiting time under normal workload | Approved timing start/end points and target; normal-load profile defined | Execute representative journeys under normal workload and collect timings | The agreed percentile/statistic meets the approved normal-load target; no averaging or exclusions conceal slow journeys | Load-test report, raw timings, percentile calculation | Technology / QA / Product Owner | High | Blocked - target definition
TC-012 | NFR-01 | AC-11 | Performance - Peak | Measure customer waiting time under peak workload | Approved timing definition/target and peak-load profile defined | Execute representative journeys at expected peak concurrency | The agreed percentile/statistic meets the approved peak-load target; failures and timeouts are separately reported | Load-test report, latency distribution, failure/timeout counts | Technology / QA / Product Owner | High | Blocked - target definition
TC-013 | NFR-02 | AC-12 | Capacity / Load | Validate capacity against expected peak workload and approved headroom | Expected peak workload, headroom percentage and measurement method approved | Run a sustained peak test and a stress/spike test | System supports approved peak workload plus approved headroom without unacceptable queue growth, resource saturation or uncontrolled errors | Capacity report, CPU/memory, queue depth/wait, throughput, errors | Technology Lead / QA | High | Blocked - capacity target
TC-014 | NFR-03 | AC-13 | Reliability | Validate processing reliability at normal and peak load | Reliability thresholds, observation window and workload profiles approved | Run normal and peak workloads; inject representative transient failures | Processing success, error, retry and timeout metrics meet approved thresholds; recovery is controlled and auditable | Reliability report, error budget/threshold calculations, event logs | Technology / QA | High | Blocked - reliability thresholds
TC-015 | NFR-04 | AC-14 | Compliance regression | Confirm optimization does not weaken mandatory compliance controls | Compliance-approved regression suite and expected decisions are available | Run mandatory, conditional, changed-state and reuse-eligible scenarios before/after optimization | All mandatory decisions remain correct; reuse occurs only under approved conditions; no bypass is introduced | Compliance regression results, audit history, sign-off | Compliance SME / QA | Critical | Not Run

## 02_UAT_Scenarios
UAT ID | Requirement ID | Business Scenario | Given | When | Then / Expected Business Outcome | Business Evidence | Business Owner | Status
UAT-01 | BR-01 | Complete a loan application end to end | Customer has a valid application and required documents; approved KPI definition exists | Customer submits the application through the complete journey | Application completes successfully and the measured completion rate is assessed against the agreed >70% target over the approved window | UAT run, KPI report and sample definition | Business Owner | Not Run
UAT-02 | FR-02 | Use an unchanged, still-valid document validation result | Document/version, rules and compliance-relevant application attributes are unchanged; prior result is valid and reuse is approved | Customer continues through a workflow transition | The eligible result is reused and the action is auditable; mandatory fresh checks still run where required | Validation history and business walkthrough | Compliance SME | Blocked - reuse rules
UAT-03 | FR-05 | Recover from a temporary processing issue | Customer has saved application information and a retryable temporary failure occurs | Customer retries or resumes after recovery becomes available | Customer continues without restarting or re-entering saved information; required checks remain enforced | Observed journey and application-state comparison | Product Owner | Not Run
UAT-04 | FR-06 | Handle a failure that cannot be automatically recovered | Automatic recovery is unsuccessful or customer action is required | Customer reaches the unresolved-failure state | Customer receives understandable status and a clear next action; application information remains saved | Message review and UAT observation | Product Owner | Blocked - message approval
UAT-05 | FR-07 | Operations investigates an unresolved failure | An unresolved document-processing failure has been recorded | Operations opens the failure context and follows the support process | Operations can identify the application/document, failure, retry history, status and reference details needed to investigate or escalate | Operations walkthrough and case evidence | Operations Lead | Not Run
UAT-06 | NFR-04 | Confirm compliance-safe optimization | Compliance-approved regression scenarios and expected outcomes are available | Business and Compliance review optimized workflow outcomes | Mandatory controls are not skipped or weakened; reuse is limited to approved eligible cases | Compliance checklist and signed result | Compliance SME | Not Run

## 03_Entry_Exit_Criteria
Type | ID | Criterion | Evidence / Notes | Status
Entry | EN-01 | Requirements and acceptance criteria are reviewed and baselined | Baseline version and approvals recorded | Required
Entry | EN-02 | Test scenarios are mapped to requirements and acceptance criteria | Master RTM and test IDs reconciled | Required
Entry | EN-03 | Test environment and representative integrations are available | Environment/version record | Required
Entry | EN-04 | Test data covers eligible and ineligible validation reuse cases | Include changed document, changed relevant attributes, rule change and expired result | Required
Entry | EN-05 | Failure classifications and retry/backoff policy are approved | Retry limits, delay/backoff and terminal states documented | Required
Entry | EN-06 | Compliance-relevant attributes and validation-result validity rules are approved | No invented validity duration; use approved rules | Required
Entry | EN-07 | Performance timing definitions, targets, load profiles and capacity/headroom are approved | Normal/peak definitions and workload assumptions recorded | Required
Entry | EN-08 | Reliability thresholds and observation window are approved | Success/error/timeout/retry thresholds documented | Required
Exit | EX-01 | All critical and high-priority tests have passed or have formally approved disposition | Execution results and defect references | Required
Exit | EX-02 | No open Severity 1 defect remains | Defect register reviewed | Required
Exit | EX-03 | All mandatory compliance scenarios pass | Compliance SME sign-off | Required
Exit | EX-04 | Customer recovery and Operations support scenarios pass | UAT evidence and owner sign-off | Required
Exit | EX-05 | Approved performance, capacity and reliability thresholds are met | Load/reliability reports | Required
Exit | EX-06 | Every in-scope requirement has traceable validation evidence | RTM includes test/UAT evidence or documented exception | Required
Exit | EX-07 | Business Owner and Compliance SME approve release readiness | Recorded approval and any accepted residual risks | Required

## 04_Defect_Severity
Severity | Definition | Examples in this project | Expected handling
S1 - Critical | Compliance breach, data integrity/security risk, or core journey unavailable with no viable workaround | Mandatory compliance validation bypassed; widespread application completion blocked; customer/application state lost in a way that prevents recovery | Stop testing/release; immediate triage and fix; retest all affected controls
S2 - High | Major requirement failure or severe customer/operations impact; workaround limited | Recovery does not work; retries cause repeated processing; peak performance misses approved target materially; Operations lacks critical diagnostic context | Prioritize before release; documented retest and impact analysis
S3 - Medium | Partial functionality/usability issue with a reasonable workaround | Unclear noncritical message; limited diagnostic field missing but case can still be investigated | Fix or formally accept with owner and rationale; regression test
S4 - Low | Cosmetic or low-impact issue that does not compromise requirements or controls | Minor layout issue or wording inconsistency with no material misunderstanding | Schedule fix; verify in appropriate regression

## 05_Validation_Coverage
Requirement ID | Requirement Summary | Acceptance Criteria | Test Case IDs | UAT IDs | Performance / Reliability Coverage | Compliance Coverage | Coverage Status
BR-01 | Restore application completion above 70% | AC-01 | TC-001 | UAT-01 | KPI validation; target definition required | Indirect | Blocked - KPI definition
FR-01 | Preserve mandatory compliance validations | AC-02 | TC-002, TC-015 | UAT-06 | As applicable | Direct | Planned
FR-02 | Reuse eligible prior validation results | AC-03, AC-04 | TC-003, TC-004 | UAT-02 | Measure avoided processing where applicable | Direct | Blocked - reuse rules
FR-03 | Avoid unnecessary duplicate processing | AC-05 | TC-005 | UAT-02 | Processing counts and latency | Indirect | Planned
FR-04 | Classify failures and apply approved recovery path | AC-06, AC-07 | TC-006, TC-007 | UAT-03 | Retry/error metrics | Compliance failure is non-retryable | Blocked - retry policy
FR-05 | Recover without restarting the whole application | AC-08 | TC-008 | UAT-03 | Journey timings as applicable | Mandatory checks remain enforced | Planned
FR-06 | Provide clear status and next action to customer | AC-09 | TC-009 | UAT-04 | Not primary performance coverage | No compliance bypass | Blocked - message approval
FR-07 | Provide Operations with sufficient failure context | AC-10 | TC-010 | UAT-05 | Failure trend monitoring supports investigation | Access controls apply | Planned
NFR-01 | Meet approved customer waiting-time targets | AC-11 | TC-011, TC-012 | — | Normal and peak load | Compliance journey included | Blocked - target definition
NFR-02 | Support peak workload plus approved headroom | AC-12 | TC-013 | — | Capacity, queue and resource measures | Compliance workload included | Blocked - capacity target
NFR-03 | Meet approved processing reliability thresholds | AC-13 | TC-014 | — | Success/error/timeout/retry measures | Compliance journey included | Blocked - reliability thresholds
NFR-04 | Do not weaken mandatory compliance controls | AC-14 | TC-015 | UAT-06 | As applicable | Direct regression | Planned