## Workload Profiles
Profile ID | Load Type | Workload Definition | Parameters to Agree | Owner(s) | Status | Evidence / Notes
LOAD-01 | Normal | Representative expected day-to-day use of the Document API. | Request rate; concurrent users/requests; document type/size mix; duration; test environment; data volume. | Technology Lead + QA + Operations | TBD — profile not approved | Use representative traffic and document mix; record assumptions and source.
LOAD-02 | Peak | Representative expected peak use, including concurrency and queueing behavior. | Peak request rate; peak concurrency; document type/size mix; duration; environment; capacity/headroom assumption. | Technology Lead + QA + Operations | TBD — profile not approved | Earlier simulation evidence indicates queueing/saturation at peak; exact test profile still needs agreement.
LOAD-03 | Recovery / resilience (if in scope) | Observe behavior during temporary queue pressure or transient service errors. | Failure injection approach if permitted; retry conditions; monitoring; recovery criteria; test safety controls. | Technology Lead + QA | Proposed — scope to confirm | Do not run failure injection in production without explicit authorization.

## Measurement & Acceptance
Item | Current Position | Decision / Definition Required | Owner(s) | Status | Traceability
API measurement boundary | Start: API receives valid request. End: corresponding response is returned. | Confirm telemetry events/timestamps, correlation ID, and treatment of errors/timeouts. | Technology Lead + QA | Definition proposed; confirm | NFR-05; TC-012
Statistic | p95 proposed as primary measure for discussion; not approved. | Approve statistic; consider whether p99 is also needed for tail latency. Ensure historical comparisons use comparable statistics. | Product/Business Owner + Technology Lead + QA | TBD — not approved | NFR-05; TC-012
Normal-load threshold | No approved threshold. | Agree threshold and rationale using business expectations, technical feasibility, and measured normal-load results. | Product/Business Owner + Technology Lead | TBD | NFR-05; TC-012
Peak-load threshold | No approved threshold. | Agree threshold and rationale using business expectations, technical feasibility, and measured peak-load results. | Product/Business Owner + Technology Lead | TBD | NFR-05; TC-012
Pass/fail rule | TC-012 blocked; criteria not approved. | Define statistic, workload, sample/run requirements, threshold(s), error/reliability criteria, and treatment of retries/timeouts. | QA + Technology + Product Owner | TBD — required before acceptance execution | TC-012; release readiness
Baseline comparability | V1 = 1.8 sec; V2 = 3.9 sec; +2.1 sec (~116.7%). | Confirm source, statistic, sample size, workload, environment, and whether figures are comparable. | Technology Lead + QA | TBD — evidence check | NFR-05; root cause analysis

## Readiness Checklist
Check ID | Preparation Check | Completion Evidence | Owner | Status | Blocks TC-012 acceptance?
PREP-01 | Normal workload profile defined and approved. | Approved profile with request rate, concurrency, document mix, duration, and environment. | Technology + QA + Operations | Open | Yes
PREP-02 | Peak workload profile defined and approved. | Approved peak profile and capacity assumptions. | Technology + QA + Operations | Open | Yes
PREP-03 | Measurement boundary and telemetry verified. | Documented timestamps/events, correlation ID, and telemetry availability. | Technology + QA | Open | Yes
PREP-04 | Statistic and threshold(s) approved. | Approved NFR-05 with statistic, normal/peak threshold(s), and rationale. | Product Owner + Technology Lead | Open | Yes
PREP-05 | Pass/fail rule approved. | Test protocol including samples/runs, reliability/error treatment, and result evaluation. | QA + Product Owner + Technology | Open | Yes
PREP-06 | Test environment and build identified. | Environment, configuration, build/version, and data setup recorded. | QA + Technology | Open | Yes
PREP-07 | Telemetry and report template ready. | Latency distribution, request volume, errors/timeouts, retries, queue/saturation indicators where available. | QA + Technology | Open | Yes
PREP-08 | Governance gate/exception interpretation recorded. | Written decision from authorized governance representative; exception route clarified if relevant. | PM / authorized governance owner | Open | Release decision dependency; does not itself define performance criteria

## Actions & Escalation
Action ID | Action / Trigger | Accountable Role | Timing | Escalation Trigger | Required Response / Evidence | Status
ACT-07-01 | Confirm whether performance acceptance is a mandatory release gate and clarify exception route. | Project Manager to identify authorized governance owner | Propose decision deadline with PM; exact date TBD | If no written governance decision by the agreed deadline, escalate to the project sponsor/governance chair through the confirmed route. | Written policy interpretation; gate status; exception route and approval authority if applicable. | Open
ACT-07-02 | Assign a named decision owner and confirm a decision deadline. | Project Manager | Proposed concrete trigger: within 1 business day of this request | If no named owner and no agreed decision deadline are recorded by end of the next business day, escalate to the project sponsor/governance chair for assignment. | Named accountable owner, agreed deadline, and recorded escalation route. | Proposed trigger — PM approval required
ACT-07-03 | Finalize NFR-05 measurement and acceptance criteria. | Product/Business Owner + Technology Lead; QA advises | Before TC-012 acceptance execution; due date TBD | If criteria remain unapproved by the agreed test-start date, notify PM and keep TC-012 blocked; escalate through project governance if release timing is affected. | Approved statistic, normal/peak profiles, thresholds, pass/fail rules, and requirement traceability. | Open
ACT-07-04 | Prepare performance test setup while decisions are pending. | QA Lead + Technology Lead | In parallel with governance and criteria work | If required telemetry, environment, or workload data is unavailable by the agreed test-preparation date, notify PM and agree remediation/owner. | Environment/build, test data, workload profile, telemetry, and report template. | Open

## Evidence & Reporting
Evidence Item | What to Capture | Why It Matters | Owner | Status
V1/V2 baseline record | V1 1.8 sec; V2 3.9 sec; statistic/source/workload/environment if available. | Supports regression analysis; does not set acceptance threshold. | Technology + QA | Known values; comparability TBD
Test run metadata | Date/time, build, environment, workload profile, request count, concurrency, document mix. | Makes the result reproducible and interpretable. | QA | Template ready; execution pending
Latency results | Chosen statistic (p95 proposed, not approved); distribution; normal/peak results. | Compare results against approved criteria. | QA + Technology | Pending approved criteria
Reliability/diagnostics | Errors, timeouts, retries, queue depth/wait and saturation metrics where available. | Avoid accepting low latency while failures or queueing remain problematic. | Technology + QA | Metrics to confirm
Decision traceability | Governance decision, requirement version, TC-012 execution ID, evidence links, approvals. | Connects governance and requirements to the test and release decision. | BA / record owner to confirm | Pending