## Performance Requirements
ID | Requirement / Decision | Definition / Proposed Approach | Current Status | Owner(s) | Evidence / Approval Needed | Traceability
NFR-05 | Document API response time | The Document API shall meet an approved response-time threshold under normal and peak workloads. Measure from receipt of a valid API request to return of the corresponding API response. Report normal- and peak-load results separately. | Draft — threshold not approved | Technology Lead; Product/Business Owner | Agree threshold, percentile/statistic, load profile, test duration, and pass/fail rule; record stakeholder approval. | Solution Requirements Mapping; RTM; TC-012
PERF-DEC-01 | Acceptance threshold | Do not automatically adopt 2 seconds or 4 seconds. V1 is a useful baseline; V2 is evidence of regression. Set the target after reviewing business expectations, technical feasibility, and measured normal- and peak-load performance. | Open decision — TBD | Product/Business Owner; Technology Lead; Sponsor as required by governance | Document the agreed threshold and rationale, including any separate normal/peak thresholds. | NFR-05; RTM; release gate
PERF-DEC-02 | Performance statistic | Choose a statistic suitable for customer experience and API behavior (recommended discussion: p95; consider p99 for tail latency). Do not treat an average alone as sufficient evidence. | Open decision — TBD | Technology Lead; QA; Product/Business Owner | Approve percentile/statistic and reporting method before acceptance testing. | NFR-05; TC-012
PERF-DEC-03 | Normal-load profile | Define representative transaction volume, concurrency, document mix, and duration for normal operating conditions. | Open decision — TBD | Technology Lead; QA; Operations | Approved workload profile and repeatable test configuration. | NFR-05; performance test plan
PERF-DEC-04 | Peak-load profile | Define expected peak concurrency, request rate, document mix, and duration, including the agreed capacity headroom assumption if approved. | Open decision — TBD | Technology Lead; QA; Operations | Approved peak workload profile and rationale for headroom. | NFR-05; capacity requirement; TC-012
PERF-DEC-05 | Evidence and reproducibility | Capture timestamped API telemetry and repeatable load-test results. Report sample size, workload, percentile, errors/timeouts, and whether results meet the approved threshold. | Proposed approach — confirm with QA/Technology | QA; Technology Lead | Test report, telemetry extracts, environment/configuration, run timestamp, and sign-off. | TC-012; release readiness

## Baseline and Measurement
Item | V1 baseline | V2 observed | Change | Interpretation / caveat
Document API response time | 1.8 sec | 3.9 sec | +2.1 sec (+116.7%) | Evidence of API latency regression. Values are baseline/observed results, not approved acceptance thresholds.
Measurement start | API receives a valid request | Same definition required | — | Use a consistent timestamp/event definition across versions and test runs.
Measurement end | API returns the corresponding response | Same definition required | — | This is API response time, not end-to-end customer waiting time.
Normal workload | To be characterized | To be measured | — | Define representative load and report results separately.
Peak workload | To be characterized | To be measured | — | Define peak concurrency/request rate and report results separately.
Statistic | Confirm if historical statistic is known | Confirm if historical statistic is known | — | Do not compare averages to percentiles. Confirm whether 1.8s and 3.9s represent the same statistic and workload.
Acceptance threshold | Not applicable | TBD | — | Requires business/technical agreement and documented approval before TC-012 can be judged pass/fail.

## Test Approach
Step | Test activity | What to capture | Pass/fail basis | Owner | Status
1 | Confirm test scope and measurement boundary | API request-received timestamp; response-returned timestamp; correlation/request ID | Consistent start/end events verified | QA + Technology | Pending
2 | Approve normal and peak workload profiles | Concurrency, request rate, document mix/size, test duration, environment | Profiles approved by accountable stakeholders | Technology + QA + Operations | Pending
3 | Approve statistic and threshold | Chosen percentile/statistic; normal/peak threshold(s); rationale | Written approval recorded; no threshold assumed from V1/V2 | Product Owner + Technology Lead | Pending
4 | Run repeatable baseline and solution tests | Multiple runs, sample count, latency distribution, errors/timeouts, retries | Test follows approved protocol and results are reproducible | QA | Pending
5 | Compare normal vs peak performance | Statistic for each load profile; saturation/queue indicators where available | Each profile meets its approved threshold and agreed error/reliability criteria | QA + Technology | Pending
6 | Attach evidence and update TC-012 | Test report, telemetry, run configuration, date/time, build/version | TC-012 status set only against approved criteria | QA | Pending
7 | Review release impact | Residual risks, monitoring/alerts, rollback readiness, approvals | Release owner applies release policy; no mandatory gate silently bypassed | Release Owner + Business/Compliance as applicable | Pending

## Open Decisions
Decision ID | Question | Why it matters | Decision owner(s) | Current position | Required output
OD-01 | What API response-time threshold applies under normal load? | Sets measurable acceptance criteria without assuming V1 is automatically acceptable. | Product/Business Owner + Technology Lead | TBD | Approved threshold and rationale
OD-02 | What API response-time threshold applies under peak load? | Peak queueing and latency are central to the observed regression. | Product/Business Owner + Technology Lead + Operations | TBD | Approved threshold and rationale
OD-03 | Which statistic is the acceptance measure (e.g., p95; p99 as tail-latency companion)? | The same statistic must be used for comparable measurements and pass/fail decisions. | Technology Lead + QA + Product/Business Owner | TBD | Approved statistic and reporting convention
OD-04 | Are the V1 1.8s and V2 3.9s figures based on the same statistic and comparable workloads? | Comparison is strongest when definitions, workload, and environments are comparable. | Technology Lead + QA | Not yet confirmed | Baseline comparability note
OD-05 | What reliability/error-rate criteria apply alongside latency? | A fast response that fails or times out may not meet the business need. | Technology Lead + QA + Product Owner | TBD | Approved reliability criteria
OD-06 | Who approves the final performance requirement and residual release risk? | Prevents a proposed target or conditional release from being treated as approved. | Follow project governance / release policy | TBD | Recorded approvals