## Decision Log
Decision ID | Decision / Question | Evidence / Context | Current Position | Decision Owner(s) | Approval / Evidence Required | Status | Traceability
DEC-PERF-01 | Is performance acceptance a mandatory release gate? | TC-012 remains blocked because the response-time acceptance target and measurement definition are not approved. | Unknown — verify the release policy and project governance before deciding whether an exception is possible. | Project Manager / Release Owner; confirm accountable authority | Policy reference or documented governance decision; record whether TC-012 is a must-pass gate. | OPEN — POLICY CHECK REQUIRED | TC-012; release readiness
DEC-PERF-02 | Who makes the release decision? | The release decision must follow project governance; BA coordinates evidence and traceability but does not independently accept release risk unless explicitly authorized. | Use the authorized release owner under project governance; confirm named role/person and approval route. | Release Owner under governance | Documented authority, decision record, and required Business/Technology/QA/Compliance input. | PENDING CONFIRMATION | Release readiness; risk acceptance
DEC-PERF-03 | Which statistic should be used for API latency acceptance? | V1 observed response time = 1.8 sec; V2 observed response time = 3.9 sec (+2.1 sec, approximately +116.7%). Comparability of workload/statistic still needs confirmation. | p95 proposed as a primary measure for discussion; not approved. Consider whether p99 is also useful for tail latency. | Technology Lead + QA + Product/Business Owner | Approve statistic, reporting convention, sample size, workload conditions, and comparability of baseline data. | PROPOSED — NOT APPROVED | NFR-05; TC-012
DEC-PERF-04 | What are the normal-load and peak-load profiles? | V2 shows a performance regression and earlier evidence indicates queueing/saturation at peak. The exact test profile is not approved in this decision record. | TBD — define concurrency, request rate, document mix/size, duration, environment, and capacity assumptions. | Technology Lead + QA + Operations | Approved, repeatable workload definitions for normal and peak conditions. | TBD | NFR-05; TC-012; capacity requirements
DEC-PERF-05 | What API response-time threshold applies under normal and peak load? | V1 1.8 sec is a baseline and V2 3.9 sec is regression evidence. Neither value automatically becomes an acceptance threshold. | TBD — agree based on business expectations, technical feasibility, and measured performance under defined loads. | Product/Business Owner + Technology Lead; QA advises testability | Approved threshold(s), rationale, statistic, workload profile, and pass/fail rule. | TBD — NO APPROVED THRESHOLD | NFR-05; RTM; TC-012
DEC-PERF-06 | Can the release proceed under an exception if TC-012 remains blocked? | Release policy and mandatory-gate status are currently unknown. Conditional release is not assumed to be permitted. | TBD — assess only after DEC-PERF-01 is resolved. Do not bypass a mandatory gate. | Authorized Release Owner under governance | Policy permits exception; explicit risk acceptance; required approvals; safeguards, monitoring, rollback, and time-bound follow-up if applicable. | TBD — DO NOT ASSUME EXCEPTION | Release readiness; risk register

## Action Register
Action ID | Action | Why / Expected Output | Owner | Dependency | Due Date | Status | Evidence to Close | Related Decision / Requirement
ACT-PERF-01 | Verify release policy and identify whether TC-012 is a mandatory release gate. | Establish whether a release exception is permitted; do not assume either answer. | Project Manager / Release Owner (confirm owner) | None | TBD | OPEN | Policy citation or recorded governance decision; named decision authority. | DEC-PERF-01; TC-012
ACT-PERF-02 | Confirm the authorized release decision-maker and required approvers. | Record decision rights and required Business, Technology, QA, and Compliance input as applicable. | Project Manager / Release Owner | ACT-PERF-01 may clarify governance | TBD | OPEN | RACI/governance reference and named approver roles. | DEC-PERF-02
ACT-PERF-03 | Define representative normal-load and peak-load test profiles. | Make performance testing repeatable and comparable. | Technology Lead + QA + Operations | Agree test environment and representative traffic/document mix | TBD | OPEN | Approved workload profile including concurrency, request rate, document mix/size, duration, and environment. | DEC-PERF-04; NFR-05; TC-012
ACT-PERF-04 | Confirm whether V1 and V2 latency figures use comparable workloads and the same statistic. | Avoid comparing unlike measurements or treating a historical average as a percentile. | Technology Lead + QA | Access to source telemetry/test reports | TBD | OPEN | Baseline comparability note with source, sample, statistic, workload, and environment. | DEC-PERF-03; NFR-05
ACT-PERF-05 | Facilitate stakeholder agreement on the latency statistic and threshold(s). | Convert NFR-05 from draft to measurable, approved acceptance criteria. | Product/Business Owner + Technology Lead; QA supports | ACT-PERF-03 and ACT-PERF-04 | TBD | OPEN | Approved NFR with statistic, normal/peak threshold(s), measurement boundaries, and rationale. | DEC-PERF-03; DEC-PERF-05; NFR-05
ACT-PERF-06 | Execute performance tests and update TC-012 against approved criteria. | Determine pass/fail using approved criteria rather than a guessed threshold. | QA Lead | ACT-PERF-03 and ACT-PERF-05 | TBD | BLOCKED — CRITERIA REQUIRED | Timestamped test report, telemetry, build/version, workload configuration, results, errors/timeouts, and sign-off. | NFR-05; TC-012
ACT-PERF-07 | Assess any proposed release exception only if policy allows it. | If applicable, record risk owner, monitoring, alert thresholds, rollback/recovery, and time-bound validation; do not bypass mandatory gates. | Authorized Release Owner; relevant approvers | ACT-PERF-01 and ACT-PERF-02 | TBD | Policy basis, explicit approval, accepted residual risks, safeguards, and review deadline. | DEC-PERF-06; release readiness

## Release Exception Assessment
Control / Question | Current Evidence | Status | Required Next Step | Decision Authority / Owner | Do Not Assume
Release policy permits an exception | Not yet verified in the simulation. | UNKNOWN — VERIFY | Check policy and record the exact rule or obtain a governance decision. | Project Manager / Release Owner | Do not assume conditional release is permitted.
TC-012 is a mandatory gate | Performance criteria are unapproved and TC-012 remains blocked. | UNKNOWN — VERIFY | Confirm gate classification and whether an approved exception route exists. | Project Manager / Release Owner / QA Lead | Do not mark TC-012 Passed without approved criteria and evidence.
Performance thresholds approved | No approved API latency threshold is recorded. | NO — TBD | Obtain business/technical agreement on statistic, normal/peak profiles, threshold(s), and pass/fail rule. | Product/Business Owner + Technology Lead; QA advises | Do not convert V1 1.8 sec or V2 3.9 sec directly into a threshold.
Workload profiles approved | Normal and peak workload definitions remain open. | NO — TBD | Approve concurrency, request rate, document mix/size, duration, environment, and capacity assumptions. | Technology Lead + QA + Operations | Do not claim a valid peak-load test without a defined profile.
Authorized risk acceptance recorded | No exception approval is evidenced. | NO EVIDENCE — TBD | If policy permits an exception, obtain documented approval from the authorized release owner and required stakeholders. | Authorized Release Owner under governance | BA recommendation is not equivalent to risk acceptance.
Monitoring and alerting ready | No approved release-specific thresholds/responders are evidenced here. | NOT EVIDENCED | If exception is permitted, define monitoring metrics, alert thresholds, responder, escalation, and review window. | Technology + Operations + Release Owner | Do not describe safeguards as ready until evidenced.
Rollback / recovery ready | No release-specific rollback evidence is recorded in this workbook. | NOT EVIDENCED | Verify rollback steps, decision triggers, responsible person, and recovery validation. | Technology + Release Owner | Do not assume a rollback plan exists because it is customary.
Time-bound follow-up validation | No due date or owner-approved deadline is recorded. | TBD | If exception is approved, set a deadline, owner, test window, and escalation if validation misses the deadline. | Release Owner + QA + Technology | Do not invent dates.
Overall assessment | Policy, criteria, approvals, and evidence are incomplete. | NOT READY TO APPROVE AN EXCEPTION ON CURRENT EVIDENCE | Resolve mandatory-gate policy first; then follow governance and document the decision. | Authorized Release Owner under governance | This is an evidence status, not a claim that policy prohibits an exception.